## Sheet1
S.No. | Projects
| Chemical Report | PPD | ELBE | NON ELBE | Cash Allocation Remit
Developement | Completed | Completed | On Hold | On Hold | Completed
Estimated time | 2 months | 2 Month | On Hold | On Hold | 4 months
Actual time | 6 months (No data for testing) | 3 Months | On Hold | On Hold | 6 months
Delays | 4 | 0 | On Hold | On Hold | 2
Number of CR's implimented - | 0 | CR - 2 (AA code not working for these two, so fixed in BP for (a) ByBU (b) ByCountry | NA | NA | 0
Number of fixes done - How many | 1 | 2 | NA | NA | 1
UAT | 1 | 1 | NA | NA | 1
Hypercare | 1 Completed | 2 Completed | NA | NA | 1 Completed
Developement |  |  | Developement Start: 04-01-2022- Projected Date: 06/06/2022
Estimated time |  |  | Estimated time : 2 months
actual time |  |  | Delay: 1 month
Delays
Number of CR's implimented - |  |  | Delay - AA bot was not giving proper results and AA code not updated and need to update two reports in BP development which delayed the Bp bot.
Number of fixes done - How many
UAT |  |  | Fixed: AA Bot is running but not giving proper output fixed the issues for two: (1) ByBU (2) ByCountry and the results generated succesfully.
Hypercare
UAT - 7/12/2022 - 7/18/2022
Hypercare: 8/8/2022 - 10/10/2022
Developement Start: 01-08-2022
Estimated time : 04-31-2022
No KT was provided
SAP data not available in ARO instance. Multiple tickets raised to clone the data from Prod to dev. After cloning still no proper data.
Delay - The SAP dev instance has no data in ARO for dev & UAT. In order to fix the problem, numerous tickets and follow-ups were created. After cloning the Prod instance into ARO still there was no data. Because the issue has not yet been resolved, we were only granted permission to use the Prod instance in DEV and UAT after 6 months.
UAT: 2 months
Hypercare: Succesfully completed on 3/3/2023
Still the issue is not resolved so we got permission after nearly 2 months to use the Prod instance in DEV and UAT also.
Developement Start: 04-01-2022- Projected Date: 06/06/2022
Estimated time : 2 months
Delay: 1 month
Issue: The AA bot wasn't showing accurate results and the AA code wasn't updated, it was earlier stopped. The BP bot was delayed because it needed to update two reports in BP development.
Fixed: Changes were done to two reports : (1) ByBU (2) ByCountry and the results generated succesfully.
UAT - 7/12/2022 - 7/18/2022
Hypercare: 8/8/2022 - 10/10/2022
The Bot was in GoLive and handed back to migration team since the input was not generated by the BP Bot.
When assigned it was in Development stage due to issues in hypercare runs.
Assigned date: 11/25/2022
Issues: It has a Syspro DLL issue that isn't the same as the AA production VM. Replaced the correct DLL from the AA team. Also bot ID was not working. After 1 month it was informed license was not renewed for this BOT ID.
UAT - 2 months
Hypercare: 1 hypercare run is pending. It will be moved to hypercare, once it has been successfully tested in debug mode in the Prod VM on 3/30/2023. |  |  |  | Shashank3113^*%_!1306
The Bot was in GoLive and handed back to migration team since the output files was not generated by the BP Bot.
When assigned it was in development stage due to issues in hypercare runs.
Assigned date: 11/25/2022
Issues: It has a Syspro DLL issue that isn't the same as the AA production VM. Replaced the correct DLL from the AA team & had issue with syspro sharepoint. Also bot ID was not working.
Delay: After 1 month it was informed license was not renewed for this BOT ID.
UAT - 2 months
Hypercare: 1 hypercare run is pending. It will be moved to hypercare, once it has been successfully tested in debug mode in the Prod VM.

## Sheet2
Sl No | Bot Name | Bot Stage | Frequency | AA bot running? | Process Complexity | Developer Name | Changes | Estimated Dates | Actual dates | Delay Reason | Number Of CR's | Number of CR Fixes
1 | State Activity Boston | Hypercare | Daily(Mon-Fri) | NO | Medium | Akshay Waybase | Boston_State_Site_Activity process is assign: 23-12-2023 |  |  | VM & Access issues & SME is not responding on time | 1 | 2:- Remove two applications which is not in use now
received Abi creds: 03-01-2023 For next 10 days there was VM issue. I changed 6 different VMs.
Dev Started: 16-01-2023 KT was pending and SME was not responding for call and emails. I took follow up for more than 10 days.
Once received KT and start development there was issues with input file.and needs to connect back with Swathi but she wans on leave for 2 weeks.
CR Is raised by Swathi on 08-03-2023
CR solved on 11-03-2023
UAT: Is started on 09-03-2023
UAT Signoff- 13-03-2023
Hypercare:27-03-2023 Four Successful runs completed today
Changes:- Macrows for UOK,UO$,9RE changed old macrows not in use now.
2 | ROA Supply order - IBIS 1.9 | Hold | Daily |  |  | Aravinth | Due to CR with AA team its in hold
3 | Namibia Cash Application | Hypercare | daily | YES | Medium | Kartheek | When Assigned The Bot is in Hypercare stage.
Project Assigned on 21-02-2023.
AA Bot is running successfully
Issues:
Having sharepoint access in the BP production environment.
Issues Fixed :
1.The python package and the syspro installed in the production VM.
2.The new Environment variables are created for the sharepoint issue.
Hyper Care status : HyperCare runs are sarted On March 30th. More couple of runs needed to receive Hypercare Signoff.
4 | ROA Supply order - IBIS 2.0 | Hold | Daily |  |  | Aravinth | Due to CR with AA team its in hold
5 | Naz Daily costing | development | Daily | NO | High | Aravinth/ Vinod | AA team is working on CR currenlty
6 | Raw Material Analysis qtrly | Go Live | Once in QTR 10:30 AM | NO | Medium | Balaji | Added new logic for Year end quarter. This is not in AA.
7 | Delivery Analysis WIP | Go Live | Quarterly 10:30 AM or 12:00 PM | NO | Medium | Balaji | Added new logic for processing WIP Inventory analysis Year End file, which bot need to process for all quarters except year end quarter. AA Logic is not working properly so developed new logic for this and also Added new logic for Year end quarter. This is not in AA
8 | NAz Recon | UAT | Mon- Fri Dailyat 7:30 pm | NO | High | Balaji | AA bot is not working as expected
Currenlty BP team is working on the fixes with SME
9 | Pre legal | hypercare | once in 6 months | No | High | Lovneesh | AA bot is not working at all for this bot, neither AA code is updated for this bot. Delays are due to inventory shortage.
Developer had the sit with the Ops and update the code as per their requirnement which indeed created a lot of delay.
10 | SCFD monthly | UAT | Monthly(wd4) | YES | Medium | Gayathri | SME's wants to continue with AA bot
11 | Naz-GRNI | hypercare | Bi-weekly | YES | Medium | Gayathri | Development started: 4 Nov 2022 |  |  | Share drive access and OLEDB issue | NA | NA
UAT started: 15 Jan 2023-10 Feb 2023
Hypercare: 11 Feb - till now
Process delayed in hypercare due to VM issues. VM don't have Share drive access, created two different tickets for that and it take long time to resolve.
Then OLEDB driver was not installed.
12 | BrandBev | Go Live | WD2, WD3, WD4 | NO | Simple | Kartheek | When Assigned 75% Development Done (Amit) Project Assigned on 17-10-2022.
Estimated Time : 31-12-2022
(No Info received regarding process) - AA Bot is not running
Issues:
1. No Proper KT and other related information.
2. SAP Data is not Available in ERO instance.
3. No proper response from the SME to validate the output of both UAT and Hypercare Outputs.
Delay - There is no data in the SAP development instance. Created multiple tickets and multiple followups to resolve the issue. Still the issue is not resolved so we got permission after nearly 2 months to use the Prod instance in DEV and UAT also.
Issues Fixed : Some part of the SAP stage development has done.
Hyper Care status : HyperCare runs are sarted from February.It is running successfully.
13 | Swazilland Cash Application | UAT | daily | YES | Medium | Kartheek | When Assigned The Bot is in Development stage.
Project Assigned on 23-11-2022.
AA Bot is not ran successfully as expected.Issue in the Python script.
Now the AA Bot is running successfully.
Issues:
1. As it is AA-BP migration, waited for the AA bot python script after the changes made.
2. No frequent input files for UAT.
3. Delay in response from the ops team.
Issues Fixed :
1.There are issues with the python script for two bank statemnets. For one bank account we have fixed then python issue.For one of the remaining statement AA team worked on that and we received the full python script on 10.01.2023
2.Time taken to install the proper python package in the Dev VM.
3.I followed up multiple times for the inputs and validating the output.
Status : Received UAT signoff after so many followups on 29.3.2023. Preparing for the Bot to be Deployed to Production.
14 | A2R Europe Fixed assets | Hypercare | Daily | YES | High | Kshitij | Currently AA bot is running for this process and BP bot had issues after blueprism version upgrade.
It came back from hypercare to development stage
Currenlty Application issues and will be able to start working on it when application team fixes the issues
This bot we have done IE to Chrome migration also.
15 | CFA weekly | Hypercare | Weekly | NO | Medium | Kshitij
16 | Pay yantra | Hypercare | Weekly | YES | High | Mithun | 1) We dont have proper BRD and recordings for development, BRD and Recording which is presented in Sharedrive, that is not updated one. We are follwed that and get Currecnt AA bot BRD and bot run Recordings to understand the flow for development. | DEV - Developement started on (3-10-2022) | DEV - Developement Completed on (02-01-2023) | 1) We dont have proper BRD and recordings for development, BRD and Recording which is presented in Sharedrive, that is not updated one. We are follwed that and get Currecnt AA bot BRD and bot run Recordings to understand the flow for development. | SME requested to add some Logics in BP Code which is not presented in AA. we didnt get proper requirments,Need clear requirement steps on new changes | No CR is Fixed. Waiting for requirement steps on new changes.
[7 empty] | 2) We dont have test datas for testing in this bot. requested and get weekly live bot run countrys datas. | UAT - UAT Started on (03 Feb, 2023) | UAT - UAT Completed on (February 15, 2023) | 2) We dont have test datas for testing in this bot. requested and get weekly live bot run countrys datas.
[7 empty] | 3) In Hypercare 1 week bot run faily due to infra issues. 1 run was successful | Hypercare - Hypercare Started on ( 20.02.2023) | Hypercare - Hypercare Started on (In Progress) | 3) In Hypercare 1 week bot run faily due to infra issues. 1 run was successful
17 | Frieghts EC | Go Live | Weekly | Yes(for partial process) | High | Rakshitha | When Assigned 15% Development Done.
Project Assigned on 12-07-2022 - ETA 31/11/2022
Development completed in 1 month
UAT it took 2 months
Hyper care runs, it took 4 months
AA Bot is running for partial process
Issues:
1. No Documentation and KT and other related information.
2. No Sharedpath access
3. Macro is not Working
4. SAP Data is not Available in ARO instance.
5. No Input Files
Delay - There are totally 5 flows in the bot, delayed on receiving all the flows by SME.
18 | Contranetting-Namibia | UAT | Daily | No | High | Rakshitha | When Assigned it is in hypercare stage. Due to CR it came back to development.
Project Assigned on 14-10-2022
Development : 2 weeks after the CR received
UAT : 3 weeks
Hyper Care started
Delay : It took two months to syspro installation and syspro UAT account Onboard.
19 | France Invoicing | Hypercare | Daily | Yes | High | Rakshitha | When assigned it is about to start UAT.
For UAT it took around 3 weeks.
HyperCare has been started.
Issue Fixed : Worked on issue in 1 flow which was there in AA too. In AA the issue is recently fixed.
Delay : Issues faced in salesforce installation in the VM, to resolve the issue it took around 1 month.
20 | Chemical report | Hypercare | Monthly | YES | High | Syed
21 | Cash Remit allocation | UAT | Weekdays | YES | Medium | Syed
22 | Excise Recon | UAT | WD6 12PM, WD7,8,9 4PM |  |  | Vinod
23 | ICF to DCF | Hypercare | Monthly(wd10) |  |  | Viswa | AA bot is not working as expected
BP team worked on the fixes and made bot run in BP
24 | Excise Forms | UAT | WD6 4PM |  |  | Viswa
25 | Third Party Payroll | Go Live | Weekly(Thursday) |  |  | Ramprasad
26 | IT2 Reporting - Unmatched Transactions | Go Live | Weekdays |  |  | Manasa
27 | IT2 Reporting - Weekly Account Recon | Go Live | Weekdays |  |  | Manasa
28 | IT2 Reporting - Weekly Account Recon (58,60,61) | Go Live | Weekdays |  |  | Manasa
29 | NAZ payroll | Go Live | Weekly |  |  | Ramprasad
30 | Ghana Cash application | Go Live | Daily |  |  | Manasa
31 | Rehabilitation | Go Live | 4 times a month(adhoc) |  |  | Lovneesh | Developement start : 17 March 2022
Estimated time : 3 months
actual time : 4 months
Delays : 1 month
Number of CR's implimented - 1 remarks code on ZUBUp2 screen which was not present on orignal AA code.
AA bot was not working at the time of development and UAT for this bot due to which there were multiple delays in BP bot development as AA code was not updated.
There was a 2 day delay from SME's end due to shortage of input items.
UAT : 25 May 2022 - 31st May 2022
Hypercare : 2 june 2022 - 10 June
32 | Uganda Cash application | Go Live | daily |  |  | krishna
33 | Journal Entries Error | Go Live | Weekdays |  |  | Manasa
34 | Cash InTransit | Go Live | Monthly |  |  | Kshitij
35 | Interest accrual | Go Live | monthly |  |  | Kshitij
36 | Cobrew AE Vs JE | Go Live | Everyday 4.30PM (Mon-Fri) |  |  | Mithun kumar
37 | PPD | Go Live | Monthly(WD8) |  |  | Syed | Developement Start: 04-01-2022- Projected Date: 06/06/2022 Estimated time : 2 months Delay: 1 month Delay - AA bot was not giving proper results and AA code not updated and need to update two reports which delayed the Bp development. Issues Fixed: AA Bot is running but not giving proper output fixed the issues for two: (1) ByBU (2) ByCountry and the results generated succesfully. UAT - 7/12/2022 - 7/18/2022 Hypercare: 8/8/2022 - 10/10/2022
38 | Cog vs It2 | Go Live | Monthly, WD10 at 4pm IST | Yes | Simple | Amit | Macro issue was fixed.
39 | zambia Cash Application | Go Live | daily |  |  | krishna
40 | Actual and Forecasting | Go Live | weekly, Tuesday 10:00 AM | Yes | High | Amit | AA bot was designed with Bex analyser. Infra team not able to fix Bex analyser in machine. Bot was designed with new logic.
41 | Raw Metarial Analysis Monthly | Go Live | WD5 9 AM |  |  | Mithun kumar
42 | CFA daily | Go Live | daily |  |  | Kshitij
43 | PTP_SA_Vendor Reconciliation | Go Live | Mon & fri | Yes | Medium | Rakshitha | When assigned it is in hypercare start state.
Hypercare it took 2 months.
Now the state of the bot is Golive.
Delay : Sap Password got expired two times in the Hypercare/Production. It took 3 weeks for setting the SAP account.